## Sheet 1 - Sprint 1 Burndown Cha
Sprint 1 Burndown Chart
| User Story | Initial Estimate | Day 1 Jan 26 | Day 2 Jan 27 | Day 3 Jan 28 | Day 4 Jan 29 | Day 5 Jan 30 | Day 6 Jan 31 | Day 7 Feb 1
Task ID
000 | As a user, I want the ability to create an account using my email address so that I can access app features | 8 |  |  |  |  | 8
001 | As a user, I want to be able to open the app so that I can use it. | 4 |  |  | 3 |  | 4
002 | As a user, I want to be able to close the open app and have my state saved so that I don't have to be using it constantly | 2 |  |  |  |  | 3
003 | As a user, I want to be able to see a map so that I can identify locations that may have issues | 2 |  |  |  |  | -2 | -5
004 | As a user, I want the app to automatically log me in if I've entered my login information before | 1 |  |  |  |  | 1
| Actual Effort | 17 | 17 | 17 | 14 | 14 | 14 | 21
| Estimated Effort | 17 | 15 | 13 | 11 | 9 | 7 | 5 | 3